## TestPlan
Test Plan ID | CURA_Healthcare_01
Application Name | CURA Healthcare Service
Application URL | https://katalon-demo-cura.herokuapp.com/
Application Type | Web Application
Testing Type | Manual Testing
Testing Approach | Black Box Testing
In Scope | Login, Appointment, Facility Selection, Healthcare Program, Appointment Details, Appointment Confirmation, Appointment History, Navigation, Logout, UI, Validation
Out of Scope | Performance Testing, Security Penetration Testing, Database Testing, API Testing
Test Objectives | Verify that the main application functions work correctly and identify defects in the application.
Test Environment | Windows 11, Google Chrome, Internet
Entry Criteria | Requirements are available, the application is accessible, the test environment is ready, and valid test credentials are available.
Exit Criteria | All planned test cases are executed and critical/high-priority defects are identified and reported.
Test Deliverables | Test Plan, Test Scenarios, Test Cases, RTM, Defect Report, Test Summary Report
Risks | Website may become unavailable during testing or application behavior may change.
Mitigation | Check the website before testing and continue testing when the application becomes available.
Prepared By | Shrutika Lakade

## TestScenario
S.No | Module | Test Scenario
1 | Login | Verify the login functionality with valid and invalid credentials
2 | Appointment | Verify the Make Appointment functionality
3 | Facility | Verify the facility selection functionality
4 | Healthcare Program | Verify the healthcare program selection
5 | Appointment Details | Verify the appointment date and comment fields
6 | Appointment Confirmation | Verify the appointment confirmation details
7 | Appointment History | Verify the appointment history functionality
8 | Navigation | Verify navigation between different pages/modules
9 | Logout | Verify the logout functionality
10 | UI & Validation | Verify UI elements, field validations, and error messages

## TestCases
S.No | Test Case ID | Module | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Status
1 | TC001 | Login | Verify login with valid credentials | Open application → Click Make Appointment → Enter username → Enter password → Click Login | Username: John Doe | User should login successfully and navigate to Make Appointment page | User logged in successfully and navigated to Make Appointment page | Pass
Password: ThisIsNotAPassword
2 | TC002 | Login | Verify login with invalid username | Enter invalid username and valid password → Click Login | Username: InvalidUser | User should not be logged in and appropriate error message should be displayed | User was not logged in, but no clear error message was displayed | Fail
Password: ThisIsNotAPassword
3 | TC003 | Login | Verify login with invalid password | Enter valid username and invalid password → Click Login | Username: John Doe | User should not be logged in | User was not logged in and remained on the login page | Pass
Password: Invalid123
4 | TC004 | Login | Verify login with blank username | Leave username blank → Enter password → Click Login | Password: ThisIsNotAPassword | User should not be logged in | User was not logged in | Pass
5 | TC005 | Login | Verify login with blank password | Enter username → Leave password blank → Click Login | Username: John Doe | User should not be logged in | User was not logged in | Pass
6 | TC006 | Login | Verify login with blank username and password | Leave both fields blank → Click Login | Blank | User should not be logged in and appropriate validation should be displayed | User was not logged in, but no validation message was displayed | Fail
7 | TC007 | Login | Verify password masking | Enter password in password field | ThisIsNotAPassword | Password should be displayed in masked format | Password was displayed in masked format | Pass
8 | TC008 | Appointment | Verify Make Appointment page | Login successfully and open appointment page | Valid credentials | Make Appointment page should be displayed | Make Appointment page was displayed correctly | Pass
9 | TC009 | Facility | Verify facility dropdown | Click Facility dropdown | N/A | Available facilities should be displayed | Available facilities were displayed | Pass
10 | TC010 | Facility | Verify facility selection | Open Facility dropdown → Select a facility | Tokyo CURA Healthcare Center | Selected facility should be displayed | Tokyo CURA Healthcare Center was displayed as selected | Pass
11 | TC011 | Appointment | Verify hospital readmission checkbox | Click Apply for hospital readmission | Checkbox | Checkbox should be selected | Checkbox was selected successfully | Pass
12 | TC012 | Healthcare Program | Verify healthcare program options | Check healthcare program section | Medicare / Medicaid / None | Available healthcare programs should be displayed | Medicare, Medicaid and None options were displayed | Pass
13 | TC013 | Healthcare Program | Verify healthcare program selection | Select Medicare | Medicare | Medicare should be selected | Medicare was selected successfully | Pass
14 | TC014 | Appointment Details | Verify visit date field | Click Visit Date field | Valid future date | Date picker should open | Date picker opened successfully | Pass
15 | TC015 | Appointment Details | Verify date selection | Select a valid date | 2026-09-30 | Selected date should be displayed | Selected date was displayed correctly | Pass
16 | TC016 | Appointment Details | Verify comment field | Enter comment | Regular checkup | Comment should be accepted | Comment was accepted successfully | Pass
17 | TC017 | Appointment | Verify appointment booking with valid data | Enter all required details → Click Book Appointment | Valid facility, program, date and comment | Appointment should be booked successfully | Appointment was booked successfully | Pass
18 | TC018 | Appointment | Verify booking without facility | Leave facility unselected → Enter remaining details → Book | Valid remaining data | Application should prevent booking without facility | Application allowed the appointment to be submitted without selecting a facility | Fail
19 | TC019 | Appointment | Verify booking without date | Enter other details → Leave date blank → Book | Valid remaining data | Application should prevent booking without required date | Application allowed the appointment to be submitted without a date | Fail
20 | TC020 | Appointment | Verify booking with empty form | Leave all fields blank → Click Book Appointment | Blank | Appointment should not be created | Appointment was not created | Pass
21 | TC021 | Confirmation | Verify appointment confirmation | Complete appointment booking | Valid appointment details | Confirmation page should be displayed | Appointment confirmation page was displayed | Pass
22 | TC022 | Confirmation | Verify facility in confirmation | Book appointment → Check confirmation | Tokyo CURA Healthcare Center | Selected facility should be displayed correctly | Selected facility was displayed correctly | Pass
23 | TC023 | Confirmation | Verify healthcare program in confirmation | Book appointment → Check confirmation | Medicare | Selected healthcare program should be displayed correctly | Medicare was displayed correctly | Pass
24 | TC024 | Confirmation | Verify appointment date in confirmation | Book appointment → Check confirmation | Valid date | Selected date should be displayed correctly | Selected date was displayed correctly | Pass
25 | TC025 | Confirmation | Verify comment in confirmation | Book appointment → Check confirmation | Regular checkup | Entered comment should be displayed correctly | Comment was not displayed in the confirmation details | Fail
26 | TC026 | History | Verify appointment history | Book appointment → Open History | Existing appointment | Newly booked appointment should be displayed in history | Appointment history page opened, but the newly booked appointment was not displayed | Fail
27 | TC027 | Navigation | Verify Home navigation | Click Home | N/A | User should navigate to Home page | User navigated to Home page successfully | Pass
28 | TC028 | Navigation | Verify appointment navigation | Open menu → Click Make Appointment | N/A | Make Appointment page should open | Make Appointment page opened successfully | Pass
29 | TC029 | Logout | Verify logout functionality | Login → Click Logout | Valid login | User should be logged out successfully | User was logged out successfully | Pass
30 | TC030 | Logout | Verify access after logout | Logout → Try accessing appointment page | N/A | User should not access protected functionality without login | Appointment page remained accessible after logout | Fail
31 | TC031 | UI | Verify login page UI | Open login page → Check labels, fields and buttons | N/A | All UI elements should be properly displayed | All login UI elements were displayed correctly | Pass
32 | TC032 | UI | Verify appointment page UI | Open appointment page | N/A | All fields and buttons should be properly aligned | Appointment fields and buttons were displayed correctly | Pass
33 | TC033 | Validation | Verify comment field with special characters | Enter special characters in comment | @#$% | Application should handle special characters appropriately | Special characters were accepted without causing an error | Pass
34 | TC034 | Validation | Verify invalid date | Try to enter/select an invalid date | Invalid/past date | Application should not allow an invalid appointment date | Application accepted the invalid date | Fail
35 | TC035 | Validation | Verify very long comment | Enter a very long comment | 500+ characters | Application should restrict or appropriately handle excessive input | Application accepted the long comment without any restriction | Fail
36 | TC036 | Session | Verify page behavior after refresh | Login → Open appointment page → Refresh browser | Valid login | Page should load without unexpected error | Appointment page loaded successfully after refresh | Pass
37 | TC037 | Browser | Verify application in Chrome | Open application in Chrome | Chrome | Application should work correctly | Application worked correctly in Chrome | Pass
38 | TC038 | Browser | Verify application in Firefox | Open application in Firefox | Firefox | Application should work correctly | Application worked correctly in Firefox | Pass
39 | TC039 | Security | Verify password is not visible | Enter password | ThisIsNotAPassword | Password should remain masked | Password remained masked | Pass
40 | TC040 | End-to-End | Verify complete appointment flow | Login → Select facility → Select program → Select date → Enter comment → Book → Verify confirmation | Valid appointment data | Complete appointment flow should work successfully | Complete appointment flow was completed successfully | Pass

## DefectReport
Bug ID | Test Case ID | Module | Application | Environment | Bug Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG-001 | TC002 | Login | CURA Healthcare Service | Windows 11 / Chrome | Error message not displayed for invalid username | 1. Open application | Appropriate error message should be displayed | User was not logged in, but no clear error message was displayed | Medium | Medium | Open
2. Click Make Appointment
3. Enter invalid username
4. Enter valid password
5. Click Login
BUG-002 | TC006 | Login | CURA Healthcare Service | Windows 11 / Chrome | Validation message not displayed for blank credentials | 1. Open Login page | Appropriate validation message should be displayed | User was not logged in, but no validation message was displayed | Medium | Medium | Open
2. Leave username blank
3. Leave password blank
4. Click Login
BUG-003 | TC018 | Appointment | CURA Healthcare Service | Windows 11 / Chrome | Appointment can be submitted without selecting facility | 1. Login | Application should prevent booking without selecting a facility | Appointment was submitted without selecting a facility | High | High | Open
2. Open Make Appointment
3. Do not select facility
4. Enter remaining details
5. Click Book Appointment
BUG-004 | TC019 | Appointment | CURA Healthcare Service | Windows 11 / Chrome | Appointment can be submitted without visit date | 1. Login | Application should prevent booking without a required date | Appointment was submitted without a visit date | High | High | Open
2. Open Make Appointment
3. Enter other details
4. Leave date blank
5. Click Book Appointment
BUG-005 | TC025 | Confirmation | CURA Healthcare Service | Windows 11 / Chrome | Comment is missing from confirmation details | 1. Login | Entered comment should be displayed in confirmation | Comment was not displayed in confirmation details | Medium | Medium | Open
2. Book an appointment
3. Enter comment
4. Submit appointment
5. Check confirmation page
BUG-006 | TC026 | History | CURA Healthcare Service | Windows 11 / Chrome | Newly booked appointment not displayed in history | 1. Login | Newly booked appointment should be displayed | Appointment history opened, but newly booked appointment was not displayed | High | High | Open
2. Book an appointment
3. Open appointment history
BUG-007 | TC030 | Logout | CURA Healthcare Service | Windows 11 / Chrome | Appointment page accessible after logout | 1. Login | User should not access protected functionality after logout | Appointment page remained accessible after logout | Critical | High | Open
2. Open appointment page
3. Logout
4. Try accessing appointment page again
BUG-008 | TC034 | Validation | CURA Healthcare Service | Windows 11 / Chrome | Invalid appointment date is accepted | 1. Login | Application should not allow an invalid appointment date | Invalid date was accepted | High | High | Open
2. Open Make Appointment
3. Select/enter invalid or past date
4. Submit appointment
BUG-009 | TC035 | Validation | CURA Healthcare Service | Windows 11 / Chrome | Comment field accepts excessive input | 1. Login | Application should restrict or appropriately handle excessive input | Application accepted 500+ characters without restriction | Low | Low | Open
2. Open Make Appointment
3. Enter 500+ characters in comment field

## SummaryReport
Module | Test Cases
Login | 7
Appointment | 7
Facility | 2
Healthcare Program | 2
Appointment Details | 3
Confirmation | 5
Appointment History | 1
Navigation | 2
Logout | 2
UI | 2
Validation | 3
Session | 1
Browser Compatibility | 2
Security | 1
End-to-End | 1
Total | 40
Test Execution Summary | Count
Total Test Cases | 40
Passed | 31
Failed | 9
Blocked | 0
Not Executed | 0
Pass Percentage | 77.5%
Fail Percentage | 22.5%

## RTM
Requirements Traceability Matrix
Req ID | Requirement Description | Module | Test Scenario ID | Test Case ID | Test Case Description | Execution Status
REQ-001 | Verify user can login with valid credentials | Login | TS-01 | TC001 | Verify login with valid username and password | Pass
REQ-001 | Verify user login functionality | Login | TS-01 | TC002 | Verify login with invalid username | Fail
REQ-001 | Verify user login functionality | Login | TS-01 | TC003 | Verify login with invalid password | Pass
REQ-001 | Verify mandatory login fields | Login | TS-01 | TC004 | Verify login with blank username | Pass
REQ-001 | Verify mandatory login fields | Login | TS-01 | TC005 | Verify login with blank password | Pass
REQ-001 | Verify mandatory login fields | Login | TS-01 | TC006 | Verify login with blank username and password | Fail
REQ-001 | Verify password security | Login | TS-01 | TC007 | Verify password is masked | Pass
REQ-002 | Verify user can access appointment page | Appointment | TS-02 | TC008 | Verify Make Appointment page is displayed | Pass
REQ-002 | Verify facility functionality | Facility | TS-03 | TC009 | Verify facility dropdown is displayed | Pass
REQ-002 | Verify facility functionality | Facility | TS-03 | TC010 | Verify user can select a facility | Pass
REQ-002 | Verify hospital readmission option | Appointment | TS-02 | TC011 | Verify hospital readmission checkbox | Pass
REQ-002 | Verify healthcare program options | Healthcare Program | TS-04 | TC012 | Verify healthcare program options are displayed | Pass
REQ-002 | Verify healthcare program selection | Healthcare Program | TS-04 | TC013 | Verify user can select healthcare program | Pass
REQ-003 | Verify appointment details | Appointment Details | TS-05 | TC014 | Verify visit date field is available | Pass
REQ-003 | Verify appointment details | Appointment Details | TS-05 | TC015 | Verify valid appointment date can be selected | Pass
REQ-003 | Verify appointment details | Appointment Details | TS-05 | TC016 | Verify comment field is available | Pass
REQ-003 | Verify appointment booking | Appointment | TS-02 | TC017 | Verify appointment can be booked with valid details | Pass
REQ-003 | Verify mandatory appointment fields | Appointment | TS-02 | TC018 | Verify appointment cannot be booked without facility | Fail
REQ-003 | Verify mandatory appointment fields | Appointment | TS-02 | TC019 | Verify appointment cannot be booked without visit date | Fail
REQ-003 | Verify appointment form validation | Appointment | TS-02 | TC020 | Verify appointment form with empty details | Pass
REQ-004 | Verify appointment confirmation | Confirmation | TS-06 | TC021 | Verify confirmation page is displayed | Pass
REQ-004 | Verify facility in confirmation | Confirmation | TS-06 | TC022 | Verify selected facility is displayed | Pass
REQ-004 | Verify healthcare program in confirmation | Confirmation | TS-06 | TC023 | Verify selected healthcare program is displayed | Pass
REQ-004 | Verify appointment date in confirmation | Confirmation | TS-06 | TC024 | Verify appointment date is displayed | Pass
REQ-004 | Verify appointment comment in confirmation | Confirmation | TS-06 | TC025 | Verify entered comment is displayed | Fail
REQ-005 | Verify appointment history | Appointment History | TS-07 | TC026 | Verify newly booked appointment appears in history | Fail
REQ-006 | Verify application navigation | Navigation | TS-08 | TC027 | Verify user can navigate to Home page | Pass
REQ-006 | Verify application navigation | Navigation | TS-08 | TC028 | Verify user can navigate to Appointment page | Pass
REQ-007 | Verify logout functionality | Logout | TS-09 | TC029 | Verify user can logout successfully | Pass
REQ-007 | Verify logout functionality | Logout | TS-09 | TC030 | Verify appointment page cannot be accessed after logout | Fail
REQ-008 | Verify application UI | UI | TS-10 | TC031 | Verify Login page UI | Pass
REQ-008 | Verify application UI | UI | TS-10 | TC032 | Verify Appointment page UI | Pass
REQ-009 | Verify input validation | Validation | TS-10 | TC033 | Verify special characters in comment field | Pass
REQ-009 | Verify date validation | Validation | TS-10 | TC034 | Verify invalid appointment date is rejected | Fail
REQ-009 | Verify comment field validation | Validation | TS-10 | TC035 | Verify very long comment is handled correctly | Fail
REQ-010 | Verify session behavior | Session | TS-08 | TC036 | Verify application behavior after page refresh | Pass
REQ-011 | Verify browser compatibility | Browser Compatibility | TS-10 | TC037 | Verify application in Chrome | Pass
REQ-011 | Verify browser compatibility | Browser Compatibility | TS-10 | TC038 | Verify application in Firefox | Pass
REQ-012 | Verify password security | Security | TS-10 | TC039 | Verify password masking/security | Pass
REQ-013 | Verify complete appointment workflow | End-to-End | TS-02 | TC040 | Verify complete appointment booking flow | Pass
Test Execution Summary
Total tast Cases | 40
Passed | 31
Failed | 9